## Pre-refresh Steps (hidden)
Sr. No. | Tcode | Action items | Responsible Team | Date | Status
1 | SMLG | Take detail screenshots of logon groups | Basis Team | Day 1
2 | AL11 | Take detail screenshots of all SAP directories | Basis Team | Day 1
3 | RZ12 | Take detail screenshots of RFC server groups | Basis Team | Day 1
4 | SM61 | Take detail screenshots of control object list | Basis Team | Day 1
5 | SM63 | Take screenshots of all operation modes | Basis Team | Day 1
6 | WE20 | Take screeshots of partner profiles with entries | Basis Team | Day 1
7 | WE21 | Take screenshots of Idoc ports | Basis Team | Day 1
8 | BD54 | Take screenshots of logical systems table | Basis Team | Day 1
9 | STRUST | Take screenshots of all certificates and export them | Basis Team | Day 1
10 | BD64 | Take screenshots of distribution model | Basis Team | Day 1
11 | DBACOCKPIT | Take screenshots of system configuration and | Basis Team | Day 1
12 | DBCO | Take screenshots of database connections | Basis Team | Day 1
13 | SCC4 | Take screenshots of clients settings | Basis Team | Day 1
14 | RZ70 | Take screenshot of SLD registration | Basis Team | Day 1
15 | SLDAPICUST | Take screenshots of SLD access data | Basis Team | Day 1
16 | SMQS | Take screenshots of qRFC monitor (OUT) | Basis Team | Day 1
17 | SMQR | Take screenshots of qRFC monitor (IN) | Basis Team | Day 1
18 | SCOT | Take screenshot of SCOT settings | Basis Team | Day 1
19 | OAC0 | Take screenshots of content repositories | Basis Team | Day 1
20 | RZ03 | Take screenshots of server states | Basis Team | Day 1
21 | RZ04 | Take screenshots of operation modes | Basis Team | Day 1
22 | SPAD | Take screenshot of printers and export | Basis Team | Day 1
23 | SMQ1 | Take screenshot of outbound queue | Basis Team | Day 1
24 | SMQ2 | Take screenshot of inbound queue | Basis Team | Day 1
25 | SLICENSE | Take screenshot of installed licenses | Basis Team | Day 1
26 | STMS | Take screenshot of TMS | Basis Team | Day 1
27 | RZ10 | Take screenshot of active profiles | Basis Team | Day 1
28 | SM37 | Take screenshots of scheduled jobs | Basis Team | Day 1
29 | SM59 | Take screenshot of RFC | Basis Team | Day 2
30 | RSRFCCHK | Run report and export | Basis Team | Day 2
31 | HTTPURLLOC | Take screenshot of table HTTPURLLOC | Basis Team | Day 2
32 | STVARV | Take full screenshot of table TVARV | Basis Team | Day 2
33 | /n/SDF/MON | Take screenshot of collected reports | Basis Team | Day 2
34 | SOAMANAGER | Take screenshotd of all Z web services | Basis Team | Day 2
35 | Users Roles | Take backup of system user roles and consultants roles | Security Team | Day 2
36 | NA | Functional Go ahead | Functional | Day 2
37 | Backup | Trigger full backup of ECQ | Amit | Day 2
38 | Backup | Trigger full backup of ECP | Amit | Day 2
39 | RZ10 | SAP* Status | Basis Team | Day 2
40 | HANA | HANA License | Basis Team | Day 2
41 | OS | Disk Space | Basis Team | Day 2
42 | SPRO | IMG setup | Basis Team | Day 2
43 | OAC3 | Archive links | Basis Team | Day 2
44 | SM30 | CRMRFCPAR table | Basis Team | Day 2
45 | SMLG | SNC Status | Basis Team | Day 2
46 | CHARM | SOLMAN config screenshots | Basis Team | Day 2
47 | SMICM | Administrator ports config | Basis Team | Day 2
48 | STMS | Transports export | Basis Team | Day 2

## Database Steps (hidden)
System | Action | Responsible Team | Date | Status
Source system | Take File Backup of Source system - System & Tenant DB | Basis Team
| Move Backup files to /software folder | Basis Team
Target system | Take File Backup of Target system - System & Tenant DB | Basis Team
| Put all jobs to Schedule Status - BTCTRNS1 | Basis Team
| Lock Users except Basis | Basis Team
| Stop AS of Target system | Basis Team
| Start recovery of Target with Source data using HANA Studio | Basis Team
| Start AS of Target system | Basis Team

## Post-Steps (hidden)
Tcode | Action items | Responsible Team | Date | Status | Remarks
SLICENSE | Install License | Basis Team
BDLS | Restore logical systems | Basis Team
SM59 | Import RFC | Basis Team
SCC8 | Import User Profile | Basis Team
SCC7 | Perform post Import steps in scc7 | Basis Team
SCC4 | Open Client for refresh post steps | Basis Team
SE06 | Perform post installation in se06 | Basis Team
AL11 | Review SAP Directories AL11 | Basis Team
STMS | TMS:- Display configuraton settings of ECQ | Basis Team
STMS | Display TMS configuration: doman controller | Basis Team
STMS | Display TMS configuration: Transport Group | Basis Team
STMS | Review of Transport Routs | Basis Team
SMLG | Maintain Logon Groups | Basis Team
WE20 | Review Partner profile | Basis Team
WE21 | Ports in Idocs processing | Basis Team
RZ12 | CCMS:RFC server group maintenance | Basis Team
ST06 | ST06 OS Monitor | Basis Team
SM37 | Review of Background jobs in released status | Basis Team
SM13 | Update Requests :SM13 | Basis Team
SM12 | Enqueue Administration : SM12 | Basis Team
SE06 | System Change Option : SE06 | Basis Team
DB02 | DB Overview : DB02 :-- System configuration, Review configuration | Basis Team
SLICENSE | SAP License , Hana license | Basis Team
BD54 | Review of logical system :- BD54 | Basis Team
SM58 | Transactional RFC's | Basis Team
SM59 | Review of RFC connection | Basis Team
SM61 | Display Control object list :- SM61 | Basis Team
RZ04 | Operation Mode | Basis Team
STRUST | Trust Manager : Display : STRUST Upload all required certificated from Backup | Basis Team
BD54 | Display Distribution Model :- BD64 | Basis Team
DBCO | Database Connections :- DBCO | Basis Team
RZ70 | Registration in System landscape Directory : RZ70 | Basis Team
SLDAPICUST | SLD Access Data : SLDAPICUST | Basis Team
FINB_TR_DEST | Update RFC destination with target system RFCs. User used RFC_USER.
SECSTORE | Secure Storage administration : SECSTORE | Basis Team
SMQR | QRFC monitor | Basis Team
SCOT | SCOT | Basis Team
RZ70 | Content Repository Overview | Basis Team
RZ10 | Review of All Profiles | Basis Team
SPAD | Spool AdministrationsSPAD | Basis Team
HTTPURLLOC | SM16/SM30 - HTTPURLLOC Table | Basis Team
SOAMANAGER | Take screenshots of all Z web services and technical users used
NA | Review all fiori and webdispatcher links | Basis Team
NA | Replace Secure folder | Basis Team
NA | File system Screenshot for SS4 Application and DB | Basis Team
NA | Testing from Functional Teams | Basis Team
NA | Unlock All dialog users of ECQ | Basis Team
NA | Reschedule Batch jobs SE38 - report BTCTRANS2 | Basis Team
NA | System copy error SID displayed of Source system issue. Execute report SLCA_GET_SYSNAME in any client In case of issue "DROP TABLE SAPHANADB.APPSYSPARAM" and restart HANA after sometime SID should be changed to target system.
BACKUP | Perform Full backup of target system | Amit

## Sheet1 (hidden)
| Pre-Refresh Phase Start | Refresh Start | Post-Refresh Start | Ready for Operation | Resource | Before | Downtime | After
Basis | 2025-02-27 | 2025-02-28 | 2025-03-06 | 2025-03-08 |  | 3 | 2 | 2
C4C | 2025-02-21 | 2025-02-28 | 2025-03-01 | 2025-03-08 |  | 3 | 1 | 5
HCM | 2025-02-26 | 2025-02-28 | 2025-03-05 | 2025-03-08 | Venkat | 3 |  | 3
Security |  | 2025-02-28 | 2025-03-07 | 2025-03-08
SD |  | 2025-02-28 |  | 2025-03-08
MM |  | 2025-02-28 |  | 2025-03-08
FICO |  | 2025-02-28 |  | 2025-03-08
PP |  | 2025-02-28 |  | 2025-03-08 |  | 3 | NA | 2
PM |  | 2025-02-28 |  | 2025-03-08

## Timelines (hidden)
Time Line
Days | Day 0 - 9 Hours | Day 1 - 9 Hours | Day 2- 9 Hours | Day 3 - 9 Hours | Day 4 - 9 Hours | Day 5 - 9 Hours | Day 6- 9 Hours | Day7 - 9 Hours
Target System ECQ/C4C
Source System ECP/C4C
Pre Refresh
Refresh
Post Refresh
Pre-refresh Steps
Full Backup
Source Backup Restore
Post- Refresh Steps
Full Backup
Functional Checks
Functional Checks
C4C Pre-Refresh Steps
C4C Refresh /BackUp

## Run Book
S. No | Phase | Activity | Duration | Start Date | End Date | System/Domain | Owner | Point of Contact | Comments
1 | Pre-Refresh Validation | Connectivity Checks | 3 hour(s) | 2025-06-03 | 2025-06-03 | CPI | Sravan | Aparna | Validated the connectivity between S/4HANA and C4C and capture the screenshots of 39 Interfaces and recorded the session while we did the config and connectivity test with Basis team
2 | Pre-Refresh Validation | Take back up of the existing iflows/urls | 2 hour(s) | 2025-07-03 | 2025-07-03 | CPI | Srvana | Aparna | Extracted the existing iflows along with urls
3 | Pre-Refresh Validation | Validating the IDOC and RFC settings | 2 hour(s) | 06/05/0225 | 06/05/0225 | PI | Sravan | Aparna | Validating the PI interfaces. Need to align with basis team and Miz Rahman
4 | Pre-Refresh Validation | 3rd party systems check (Maxoptra, NeTIX/NETEDI) | 2 hour(s) | 06/05/0225 | 06/05/0225 | PI | Sravan | Aparna
5 | Pre-Refresh Validation | Communicate to RAKC for business sceanrios validations | 10 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Sent an email for business scanrios confirmation.
6 | Pre-Refresh Validation | Access to SAP & Basic Tcodes execution | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
7 | Pre-Refresh Validation | Hiring action | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
8 | Pre-Refresh Validation | Org Reassignment actions | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
9 | Pre-Refresh Validation | Master Data modifications and updates & save | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
10 | Pre-Refresh Validation | Hol Cal availability and its internal details | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
11 | Pre-Refresh Validation | WSR details | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
12 | Pre-Refresh Validation | Absence details report | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
13 | Pre-Refresh Validation | some Z reports execution | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
14 | Pre-Refresh Validation | Basic tables checking and their accessibility | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
15 | Pre-Refresh Validation | Infotypes maintenance | 30 minute(s) | 2025-05-03 | 2025-05-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
16 | Pre-Refresh Validation | Payroll Results | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
17 | Pre-Refresh Validation | Payroll simulation | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
18 | Pre-Refresh Validation | PY run -sample | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
19 | Pre-Refresh Validation | PY outcome/ results checking | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
20 | Pre-Refresh Validation | Time Evaluation - sample | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
21 | Pre-Refresh Validation | PY areas availability and maintenance | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
22 | Pre-Refresh Validation | Additional infotypes | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
23 | Pre-Refresh Validation | Recurring payments | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
24 | Pre-Refresh Validation | Payroll parameters | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
25 | Pre-Refresh Validation | Payroll periods checking | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
26 | Pre-Refresh Validation | Time & WSR details | 30 minute(s) | 2025-06-03 | 2025-06-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
27 | Pre-Refresh Validation | Time events, absences etc | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
28 | Pre-Refresh Validation | All relevant roles/auth checking for key users | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
29 | Pre-Refresh Validation | Emp Grades & text checking | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
30 | Pre-Refresh Validation | Flexible employee data rep | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
31 | Pre-Refresh Validation | Wagetype reporter | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
32 | Pre-Refresh Validation | Communication IT details checking | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
33 | Pre-Refresh Validation | Sample subtype checking for some IT | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
34 | Pre-Refresh Validation | Checking some ZHR programs | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
35 | Pre-Refresh Validation | PA* table details | 30 minute(s) | 2025-07-03 | 2025-07-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
36 | Pre-Refresh Validation | Create/Change /display Bill of Material | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
37 | Pre-Refresh Validation | Display Multilevel BOM | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
38 | Pre-Refresh Validation | BOM where-used List | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
39 | Pre-Refresh Validation | Creare/change /display WorkCenter | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
40 | Pre-Refresh Validation | Create/change/display Routing | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
41 | Pre-Refresh Validation | Create/Change/Display Production Version | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
42 | Pre-Refresh Validation | Create/change/dispaly Batch | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
43 | Pre-Refresh Validation | Create/change/display Production Order (Also Release ,TECO) | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
44 | Pre-Refresh Validation | Confirm the Production order - Operation wise | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
45 | Pre-Refresh Validation | Confirm the Production order - Order wise | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
46 | Pre-Refresh Validation | Goods Issue to production order | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
47 | Pre-Refresh Validation | Goods Receipt for Production Order | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
48 | Pre-Refresh Validation | Cancel Confirmation of Production Order | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
49 | Pre-Refresh Validation | Display Production order confirmation | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
50 | Pre-Refresh Validation | Production order information system | 30 minute(s) | 2025-05-03 | 2025-05-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
51 | Pre-Refresh Validation | Production Order Predefined Processes execution | 30 minute(s) | 2025-06-03 | 2025-06-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
52 | Pre-Refresh Validation | Reprocessing Production Order Confirmations | 30 minute(s) | 2025-06-03 | 2025-06-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
53 | Pre-Refresh Validation | Reprocessing Production Order Actual Costs | 30 minute(s) | 2025-06-03 | 2025-06-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
54 | Pre-Refresh Validation | Reprocessing Production Order Goods Movements | 30 minute(s) | 2025-06-03 | 2025-06-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
55 | Pre-Refresh Validation | Massprocessig of Production Orders | 30 minute(s) | 2025-06-03 | 2025-06-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
56 | Pre-Refresh Validation | Production Order Entry Creation for Tiles (Order Creation/Confirm/GR Reversal/Delete) | 30 minute(s) | 2025-06-03 | 2025-06-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
57 | Pre-Refresh Validation | Validation,Distribution,Posting of Prodcution Orders for Tiles (Including Reversal of Posting,Distribution and Validation) | 30 minute(s) | 2025-06-03 | 2025-06-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
58 | Pre-Refresh Validation | BOM Exception Report | 30 minute(s) | 2025-06-03 | 2025-06-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
59 | Pre-Refresh Validation | Report for prod report_tiles_LTP | 30 minute(s) | 2025-06-03 | 2025-06-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
60 | Pre-Refresh Validation | Production Statistics | 30 minute(s) | 2025-06-03 | 2025-06-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
61 | Pre-Refresh Validation | Production Report Tiles | 30 minute(s) | 2025-06-03 | 2025-06-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
62 | Pre-Refresh Validation | Production Order Execution for Sanitaryware Creation (Order Creation/Confirm/GR Reversal/Delete) | 30 minute(s) | 2025-07-03 | 2025-07-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
63 | Pre-Refresh Validation | Production Entry details -Validation/Distrubution/Posting - Sanitaryware (Including Reversal of Posting,Distribution and Validation) | 30 minute(s) | 2025-07-03 | 2025-07-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
64 | Pre-Refresh Validation | Production Entry report Sanitaryware | 30 minute(s) | 2025-07-03 | 2025-07-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
65 | Pre-Refresh Validation | Maintenance Plan create/change for SW Plant | 20 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
66 | Pre-Refresh Validation | Breakdown Order creation and execution for SW plant | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
67 | Pre-Refresh Validation | Preventive Maintenance order creation and execution for SW Plant | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
68 | Pre-Refresh Validation | Mould change order for SW plant | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
69 | Pre-Refresh Validation | Goods movement against order requirement for SW | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
70 | Pre-Refresh Validation | Material reservation through order for SW | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
71 | Pre-Refresh Validation | Malfunction notifications (used for Vehicles) create/change for SW | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
72 | Pre-Refresh Validation | Breakdown notification create/change for India region plants | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
73 | Pre-Refresh Validation | Breakdown order create/change for India region plants | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
74 | Pre-Refresh Validation | Preventive order create/change for India region plants | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
75 | Pre-Refresh Validation | Consumable GR for all regions. | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
76 | Pre-Refresh Validation | Break down Asset settlement for India region | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
77 | Pre-Refresh Validation | Malfunction notifications(used for Vehicles)create/change for TW | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
78 | Pre-Refresh Validation | Breakdown order create/change for TW | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
79 | Pre-Refresh Validation | Preventive order create/change for TW | 30 minute(s) | 2025-05-03 | 2025-05-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
80 | Pre-Refresh Validation | Calibration order create/change for TW | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
81 | Pre-Refresh Validation | Repair order create/change for TW | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
82 | Pre-Refresh Validation | Goods movement issue against order for TW | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
83 | Pre-Refresh Validation | Malfunction notifications (used for Vehicles) order create/change for TW | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
84 | Pre-Refresh Validation | Breakdown notification create/change for Tiles plant | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
85 | Pre-Refresh Validation | Breakdown order create/change for Tiles plant | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
86 | Pre-Refresh Validation | Preventive order create/change for Tiles plant | 30 minute(s) | 2025-06-03 | 2025-06-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
87 | Pre-Refresh Validation | Consumable issue for Tiles plants | 30 minute(s) | 2025-07-03 | 2025-07-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
88 | Pre-Refresh Validation | Break down Asset settlement for Tiles plant | 30 minute(s) | 2025-07-03 | 2025-07-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
89 | Pre-Refresh Validation | Goods movement against order requirement for Tiles plant | 30 minute(s) | 2025-07-03 | 2025-07-03 | PM | Nikhil Gaikwad | Nikhil Gaikwad | Verify the business scenarios and take a screenshot of the operational conditions.
90 | Pre-Refresh Validation | 01-Goods Receipt Insp. for Purchase Order | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
91 | Pre-Refresh Validation | CPL- Customer complain inspection. | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
92 | Pre-Refresh Validation | FQC- Finish Good Inspection | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
93 | Pre-Refresh Validation | Goods Movement | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
94 | Pre-Refresh Validation | Vendor Rel. Defect | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
95 | Pre-Refresh Validation | Material-Rel. Defect | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
96 | Pre-Refresh Validation | 01-Goods Receipt Insp. for Purchase Order | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
97 | Pre-Refresh Validation | 05-Inspection for customer return | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
98 | Pre-Refresh Validation | CPL- Customer complain inspection. | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
99 | Pre-Refresh Validation | FQC- Finish Good Inspection | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
100 | Pre-Refresh Validation | Goods Movement | 30 minute(s) | 2025-05-03 | 2025-05-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
101 | Pre-Refresh Validation | Vendor Rel. Defect | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
102 | Pre-Refresh Validation | Material-Rel. Defect | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
103 | Pre-Refresh Validation | 01-Goods Receipt Insp. for Purchase Order | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
104 | Pre-Refresh Validation | 05-Inspection for customer return | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
105 | Pre-Refresh Validation | CPL- Customer complain inspection. | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
106 | Pre-Refresh Validation | FQC- Finish Good Inspection | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
107 | Pre-Refresh Validation | Goods Movement | 30 minute(s) | 2025-06-03 | 2025-06-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
108 | Pre-Refresh Validation | Gone through the detail test scripts | 3 hour(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Rakhi Masand | Verify the business scenarios and take a screenshot of the operational conditions.
109 | Pre-Refresh Validation | Sent Test scripts for scenario confirmation to SME | 5 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Rakhi Masand | Verify the business scenarios and take a screenshot of the operational conditions.
110 | Pre-Refresh Validation | GL Account Master | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
111 | Pre-Refresh Validation | Park Documents & Post Parked Documents | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
112 | Pre-Refresh Validation | FI Focument Posting (JV) | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
113 | Pre-Refresh Validation | Recurring Entries, Accruals | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
114 | Pre-Refresh Validation | GL Reports, Financial Reports | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
115 | Pre-Refresh Validation | Vendor Master | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
116 | Pre-Refresh Validation | Vendor Invoice parking - Without PO | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
117 | Pre-Refresh Validation | Vendor Invoice posting - With PO | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
118 | Pre-Refresh Validation | Full Payment | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
119 | Pre-Refresh Validation | Partial payment | 30 minute(s) | 2025-05-03 | 2025-05-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
120 | Pre-Refresh Validation | Down Payment Request | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
121 | Pre-Refresh Validation | Advance/Down payment | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
122 | Pre-Refresh Validation | Advance/Down payment clearing | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
123 | Pre-Refresh Validation | Debit/Credit memo - without PO | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
124 | Pre-Refresh Validation | Vendor Clearing | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
125 | Pre-Refresh Validation | AP Reports | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
126 | Pre-Refresh Validation | Customer Master | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
127 | Pre-Refresh Validation | Customer Down payment and Security Deposit | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
128 | Pre-Refresh Validation | Customer Receipts | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
129 | Pre-Refresh Validation | AR Reports | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
130 | Pre-Refresh Validation | Bank Master | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
131 | Pre-Refresh Validation | Bank Reconciliation | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
132 | Pre-Refresh Validation | Cheque Management | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
133 | Pre-Refresh Validation | Cash Transaction | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
134 | Pre-Refresh Validation | Extended Withholding Tax (TDS) | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
135 | Pre-Refresh Validation | Asset Master | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
136 | Pre-Refresh Validation | Asset Acquisition | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
137 | Pre-Refresh Validation | Assets Transfer | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
138 | Pre-Refresh Validation | Asset Retirement | 30 minute(s) | 2025-06-03 | 2025-06-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
139 | Pre-Refresh Validation | Asset Depreciation | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
140 | Pre-Refresh Validation | Asset Reports | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
141 | Pre-Refresh Validation | FI Month End Closing Elements-Period Open/Close | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
142 | Pre-Refresh Validation | FI Month End Closing Elements-Assets | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
143 | Pre-Refresh Validation | Cost Element | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
144 | Pre-Refresh Validation | Cost Center | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
145 | Pre-Refresh Validation | Internal Order | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
146 | Pre-Refresh Validation | Profit Center | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
147 | Pre-Refresh Validation | Cost Center Reports | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
148 | Pre-Refresh Validation | Running All Z Reports | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
149 | Pre-Refresh Validation | Table level check | 30 minute(s) | 2025-07-03 | 2025-07-03 | FICO | Rakhi Masand | Vinod Yaram | Extract the table date, to get the tables names from Amit / Shalaka that is provided in SNOTE
150 | Post-Refresh Validation | Post Re-Refresh - Executing the Test scripts | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
151 | Post-Refresh Validation | GL Account Master | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
152 | Post-Refresh Validation | Park Documents & Post Parked Documents | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
153 | Post-Refresh Validation | FI Focument Posting (JV) | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
154 | Post-Refresh Validation | Recurring Entries, Accruals | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
155 | Post-Refresh Validation | GL Reports, Financial Reports | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
156 | Post-Refresh Validation | Vendor Master | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
157 | Post-Refresh Validation | Vendor Invoice parking - Without PO | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
158 | Post-Refresh Validation | Vendor Invoice posting - With PO | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
159 | Post-Refresh Validation | Full Payment | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
160 | Post-Refresh Validation | Partial payment | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
161 | Post-Refresh Validation | Down Payment Request | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
162 | Post-Refresh Validation | Advance/Down payment | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
163 | Post-Refresh Validation | Advance/Down payment clearing | 30 minute(s) | 2025-10-03 | 2025-10-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
164 | Post-Refresh Validation | Debit/Credit memo - without PO | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
165 | Post-Refresh Validation | Vendor Clearing | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
166 | Post-Refresh Validation | AP Reports | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
167 | Post-Refresh Validation | Customer Master | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
168 | Post-Refresh Validation | Customer Down payment and Security Deposit | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
169 | Post-Refresh Validation | Customer Receipts | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
170 | Post-Refresh Validation | AR Reports | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
171 | Post-Refresh Validation | Bank Master | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
172 | Post-Refresh Validation | Bank Reconciliation | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
173 | Post-Refresh Validation | Cheque Management | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
174 | Post-Refresh Validation | Cash Transaction | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
175 | Post-Refresh Validation | Extended Withholding Tax (TDS) | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
176 | Post-Refresh Validation | Asset Master | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
177 | Post-Refresh Validation | Asset Acquisition | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
178 | Post-Refresh Validation | Assets Transfer | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
179 | Post-Refresh Validation | Asset Retirement | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
180 | Post-Refresh Validation | Asset Depreciation | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
181 | Post-Refresh Validation | Asset Reports | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
182 | Post-Refresh Validation | FI Month End Closing Elements-Period Open/Close | 30 minute(s) | 2025-11-03 | 2025-11-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
183 | Post-Refresh Validation | FI Month End Closing Elements-Assets | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Hiren Rana | Verify the business scenarios and take a screenshot of the operational conditions.
184 | Post-Refresh Validation | Cost Element | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
185 | Post-Refresh Validation | Cost Center | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
186 | Post-Refresh Validation | Internal Order | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
187 | Post-Refresh Validation | Profit Center | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
188 | Post-Refresh Validation | Cost Center Reports | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
189 | Post-Refresh Validation | Running All Z Reports | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Verify the business scenarios and take a screenshot of the operational conditions.
190 | Post-Refresh Validation | Send confirmation to stakeholders | 5 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Rakhi Masand | Verify the business scenarios and take a screenshot of the operational conditions.
191 | Post-Refresh Validation | Table level check | 30 minute(s) | 2025-12-03 | 2025-12-03 | FICO | Rakhi Masand | Vinod Yaram | Extract the table date and compare the tables and it should have the data more than earlier
192 | Pre-Refresh Validation | Take detail screenshots of logon groups | 5 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
193 | Pre-Refresh Validation | Take detail screenshots of all SAP directories | 5 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
194 | Pre-Refresh Validation | Take detail screenshots of RFC server groups | 5 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
195 | Pre-Refresh Validation | Take detail screenshots of control object list | 15 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
196 | Pre-Refresh Validation | Take screenshots of all operation modes | 10 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
197 | Pre-Refresh Validation | Take screeshots of partner profiles with entries | 240 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
198 | Pre-Refresh Validation | Take screenshots of Idoc ports | 30 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
199 | Pre-Refresh Validation | Take screenshots of logical systems table | 15 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
200 | Pre-Refresh Validation | Take screenshots of all certificates and export them | 30 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
201 | Pre-Refresh Validation | Take screenshots of distribution model | 30 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
202 | Pre-Refresh Validation | Take screenshots of system configuration and | 10 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
203 | Pre-Refresh Validation | Take screenshots of database connections | 10 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
204 | Pre-Refresh Validation | Take screenshots of clients settings | 15 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
205 | Pre-Refresh Validation | Take screenshot of SLD registration | 10 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
206 | Pre-Refresh Validation | Take screenshots of SLD access data | 10 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
207 | Pre-Refresh Validation | Take screenshots of qRFC monitor (OUT) | 5 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
208 | Pre-Refresh Validation | Take screenshots of qRFC monitor (IN) | 5 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
209 | Pre-Refresh Validation | Take screenshot of SCOT settings | 30 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
210 | Pre-Refresh Validation | Take screenshots of content repositories | 10 minute(s) | 2025-03-05 | 2025-03-05 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
211 | Pre-Refresh Validation | Take backup of roles & access for capgemini team and CM | 120 minute(s) | 2025-03-05 | 2025-03-05 | S & A | Pradeep/Sai | Pradeep | Verify the business scenarios and take a screenshot of the operational conditions.
212 | Pre-Refresh Validation | Take screenshots of server states | 10 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
213 | Pre-Refresh Validation | Take screenshots of operation modes | 10 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
214 | Pre-Refresh Validation | Take screenshot of printers and export | 10 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
215 | Pre-Refresh Validation | Take screenshot of outbound queue | 5 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
216 | Pre-Refresh Validation | Take screenshot of inbound queue | 5 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
217 | Pre-Refresh Validation | Take screenshot of installed licenses | 5 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
218 | Pre-Refresh Validation | Take screenshot of TMS | 30 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
219 | Pre-Refresh Validation | Take screenshot of active profiles | 15 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
220 | Pre-Refresh Validation | Take screenshots of scheduled jobs | 30 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
221 | Pre-Refresh Validation | Take screenshot of RFC | 60 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
222 | Pre-Refresh Validation | Run report and export | 30 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
223 | Pre-Refresh Validation | Take screenshot of table HTTPURLLOC | 30 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
224 | Pre-Refresh Validation | Take full screenshot of table TVARV | 120 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
225 | Pre-Refresh Validation | Take screenshot of collected reports SDF MON | 10 minute(s) | 2025-03-06 | 2025-03-06 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
226 | Pre-Refresh Validation | Take screenshotd of all Z web services | 180 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
227 | Pre-Refresh Validation | Take backup of system user roles and consultants roles | 120 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
228 | Pre-Refresh Validation | Trigger full backup of ECQ | 240 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
229 | Pre-Refresh Validation | Trigger full backup of ECP | 240 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
230 | Pre-Refresh Validation | SAP* Status | 5 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
231 | Pre-Refresh Validation | HANA License | 5 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
232 | Pre-Refresh Validation | Disk Space | 60 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
233 | Pre-Refresh Validation | All services | 180 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
234 | Pre-Refresh Validation | CRMRFCPAR table | 15 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
235 | Pre-Refresh Validation | SNC Status | 15 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
236 | Pre-Refresh Validation | SOLMAN config screenshots | 30 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
237 | Pre-Refresh Validation | Administrator ports config SMICM | 15 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
238 | Pre-Refresh Validation | Transports export | 30 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
239 | Pre-Refresh Validation | SAPOSCOL | 15 minute(s) | 2025-03-07 | 2025-03-07 | Basis | Shalaka/Shramik | Shalaka/Shramik | Verify the business scenarios and take a screenshot of the operational conditions.
240 | Data Refresh | Take File Backup of Source system - System & Tenant DB | 240 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik | 15 hours approx for data refresh
241 | Data Refresh | Move Backup files to shared folder | 30 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
242 | Data Refresh | Take File Backup of Target system - System & Tenant DB | 240 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
243 | Data Refresh | Put all jobs to Schedule Status - BTCTRNS1 | 5 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
244 | Data Refresh | Lock Users except Basis | 15 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
245 | Data Refresh | Export tables using SCOS for target system | 30 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
246 | Data Refresh | Stop AS of Target system | 10 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
247 | Data Refresh | Start recovery of Target with Source data using HANA Studio | 300 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
248 | Data Refresh | Import tables using SCOS for target system | 180 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
249 | Data Refresh | Start AS of Target system | 15 minute(s) | 2025-03-08 | 2025-03-08 | Basis | Shalaka/Shramik | Shalaka/Shramik
250 | Post-Refresh Validation | Install License | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
251 | Post-Refresh Validation | Restore logical systems | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
252 | Post-Refresh Validation | Import RFC | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
253 | Post-Refresh Validation | Import User Profile | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
254 | Post-Refresh Validation | Open Client for refresh post steps | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
255 | Post-Refresh Validation | Perform post installation in se06 | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
256 | Post-Refresh Validation | Review SAP Directories AL11 | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
257 | Post-Refresh Validation | TMS:- Display configuraton settings of ECQ | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
258 | Post-Refresh Validation | Display TMS configuration: doman controller | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
259 | Post-Refresh Validation | Display TMS configuration: Transport Group | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
260 | Post-Refresh Validation | Review of Transport Routs | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
261 | Post-Refresh Validation | Maintain Logon Groups | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
262 | Post-Refresh Validation | Review Partner profile | 120 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
263 | Post-Refresh Validation | Ports in Idocs processing | 120 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
264 | Post-Refresh Validation | CCMS:RFC server group maintenance | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
265 | Post-Refresh Validation | ST06 OS Monitor | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
266 | Post-Refresh Validation | Review of Background jobs in released status | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
267 | Post-Refresh Validation | Update Requests :SM13 | 5 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
268 | Post-Refresh Validation | Enqueue Administration : SM12 | 5 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
269 | Post-Refresh Validation | System Change Option : SE06 | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
270 | Post-Refresh Validation | DB Overview : DB02 :-- System configuration, Review configuration | 30 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
271 | Post-Refresh Validation | SAP License , Hana license | 10 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
272 | Post-Refresh Validation | Review of logical system :- BD54 | 20 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
273 | Post-Refresh Validation | Transactional RFC's | 15 minute(s) | 2025-03-09 | 2025-03-09 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
274 | Post-Refresh Validation | Review of RFC connection | 60 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
275 | Post-Refresh Validation | Display Control object list :- SM61 | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
276 | Post-Refresh Validation | Operation Mode | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
277 | Post-Refresh Validation | Trust Manager : Display : STRUST Upload all required certificated from Backup | 30 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
278 | Post-Refresh Validation | Display Distribution Model :- BD64 | 30 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
279 | Post-Refresh Validation | Database Connections :- DBCO | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
280 | Post-Refresh Validation | Registration in System landscape Directory : RZ70 | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
281 | Post-Refresh Validation | SLD Access Data : SLDAPICUST | 10 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
282 | Post-Refresh Validation | Secure Storage administration : SECSTORE | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
283 | Post-Refresh Validation | QRFC monitor | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
284 | Post-Refresh Validation | SCOT | 30 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
285 | Post-Refresh Validation | Content Repository Overview | 30 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
286 | Post-Refresh Validation | Review of All Profiles | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
287 | Post-Refresh Validation | Spool AdministrationsSPAD | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
288 | Post-Refresh Validation | SM16/SM30 - HTTPURLLOC Table | 15 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
289 | Post-Refresh Validation | Review of all Z web services and technical users used | 60 minute(s) | 2025-03-10 | 2025-03-10 | Basis | Shalaka/Shramik | Shalaka/Shramik | Compare and validate with pre refresh screenshots.
290 | Pre-Refresh Validation | Sales order replicated in S/4 | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
291 | Pre-Refresh Validation | CHECK FREE STOCK IN ZP_BATCH_STOCK REPORT FOR RELEVANT PACKCODE AND BATCH, IF STOCK IS AVAILABLE THEN DO RESERVATION | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
292 | Pre-Refresh Validation | Check and click on posting button, system will generate posting document number | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
293 | Pre-Refresh Validation | confirm qty in sales order, | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
294 | Pre-Refresh Validation | If there is credit check system will check for credit release | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
295 | Pre-Refresh Validation | Credit release sales order | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
296 | Pre-Refresh Validation | Create delivery with reference to sales order and do PGI | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
297 | Pre-Refresh Validation | Create sales invoice with reference to delivery number | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
298 | Pre-Refresh Validation | Accounting document of invoice | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
299 | Pre-Refresh Validation | Document flow of sales order -- invoice | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
300 | Pre-Refresh Validation | Print invoice | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
301 | Pre-Refresh Validation | ADD SALES ORDER IN LOADING PLAN | 30 minute(s) | 2025-05-03 | 2025-05-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
302 | Pre-Refresh Validation | QTY CONFIRM WITH WAREHOUSE | 30 minute(s) | 2025-06-03 | 2025-06-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
303 | Pre-Refresh Validation | VEHICLE PLAN | 30 minute(s) | 2025-06-03 | 2025-06-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
304 | Pre-Refresh Validation | Delivery note created | 30 minute(s) | 2025-06-03 | 2025-06-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
305 | Post-Refresh Validation | 01-Goods Receipt Insp. for Purchase Order | 30 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
306 | Post-Refresh Validation | CPL- Customer complain inspection. | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
307 | Post-Refresh Validation | FQC- Finish Good Inspection | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
308 | Post-Refresh Validation | Goods Movement | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
309 | Post-Refresh Validation | Vendor Rel. Defect | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
310 | Post-Refresh Validation | Material-Rel. Defect | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
311 | Post-Refresh Validation | 01-Goods Receipt Insp. for Purchase Order | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
312 | Post-Refresh Validation | 05-Inspection for customer return | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
313 | Post-Refresh Validation | CPL- Customer complain inspection. | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
314 | Post-Refresh Validation | FQC- Finish Good Inspection | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
315 | Post-Refresh Validation | Goods Movement | 50 minute(s) | 2025-10-03 | 2025-10-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
316 | Post-Refresh Validation | Vendor Rel. Defect | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
317 | Post-Refresh Validation | Material-Rel. Defect | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
318 | Post-Refresh Validation | 01-Goods Receipt Insp. for Purchase Order | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
319 | Post-Refresh Validation | 05-Inspection for customer return | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
320 | Post-Refresh Validation | CPL- Customer complain inspection. | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
321 | Post-Refresh Validation | FQC- Finish Good Inspection | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
322 | Post-Refresh Validation | Goods Movement | 50 minute(s) | 2025-11-03 | 2025-11-03 | QM | Poonam Pednekar | Poonam Pednekar | Verify the business scenarios and take a screenshot of the operational conditions.
323 | Post-Refresh Validation | Access to SAP & Basic Tcodes execution | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
324 | Post-Refresh Validation | Hiring action | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
325 | Post-Refresh Validation | Org Reassignment actions | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
326 | Post-Refresh Validation | Master Data modifications and updates & save | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
327 | Post-Refresh Validation | Hol Cal availability and its internal details | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
328 | Post-Refresh Validation | WSR details | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
329 | Post-Refresh Validation | Absence details report | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
330 | Post-Refresh Validation | some Z reports execution | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
331 | Post-Refresh Validation | Basic tables checking and their accessibility | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
332 | Post-Refresh Validation | Infotypes maintenance | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
333 | Post-Refresh Validation | Payroll Results | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
334 | Post-Refresh Validation | Payroll simulation | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
335 | Post-Refresh Validation | PY run -sample | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
336 | Post-Refresh Validation | PY outcome/ results checking | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
337 | Post-Refresh Validation | Time Evaluation - sample | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
338 | Post-Refresh Validation | PY areas availability and maintenance | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
339 | Post-Refresh Validation | Additional infotypes | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
340 | Post-Refresh Validation | Recurring payments | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
341 | Post-Refresh Validation | Payroll parameters | 30 minute(s) | 2025-10-03 | 2025-10-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
342 | Post-Refresh Validation | Payroll periods checking | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
343 | Post-Refresh Validation | Time & WSR details | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
344 | Post-Refresh Validation | Time events, absences etc | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
345 | Post-Refresh Validation | All relevant roles/auth checking for key users | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
346 | Post-Refresh Validation | Emp Grades & text checking | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
347 | Post-Refresh Validation | Flexible employee data rep | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
348 | Post-Refresh Validation | Wagetype reporter | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
349 | Post-Refresh Validation | Communication IT details checking | 30 minute(s) | 2025-11-03 | 2025-11-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
350 | Post-Refresh Validation | Sample subtype checking for some IT | 30 minute(s) | 2025-12-03 | 2025-12-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
351 | Post-Refresh Validation | Checking some ZHR programs | 30 minute(s) | 2025-12-03 | 2025-12-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
352 | Post-Refresh Validation | PA* table details | 30 minute(s) | 2025-12-03 | 2025-12-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
353 | Post-Refresh Validation | Convey the successful completion of validations. | 10 minute(s) | 2025-12-03 | 2025-12-03 | HCM | Venkat | Venkat | Verify the business scenarios and take a screenshot of the operational conditions.
354 | Pre-Refresh Validation | Validate Open Activities | 1 Day(s) | 2025-05-03 | 2025-05-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
355 | Pre-Refresh Validation | Validate Communication Arrangements | 1 Day(s) | 2025-06-03 | 2025-06-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
356 | Pre-Refresh Validation | Lead Creation and Conversion to Account | 1 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
357 | Pre-Refresh Validation | Creation of opportunity from the account | 1 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
358 | Pre-Refresh Validation | Creation of Sales Quote | 1 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
359 | Pre-Refresh Validation | External Pricing from the Sales Quote | 1 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
360 | Pre-Refresh Validation | Sales Order Creation | 1 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
361 | Pre-Refresh Validation | External Pricing from the Sales Order | 2 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
362 | Pre-Refresh Validation | Transfer the Sales Order | 2 hour(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
363 | Pre-Refresh Validation | Convey the successful completion of validations. | 10 minute(s) | 2025-07-03 | 2025-07-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
364 | Post-Refresh Validation | Set up Communication Arrangements | 1.5 Day(s) | 2025-10-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
365 | Post-Refresh Validation | Lead Creation and Conversion to Account | 1 hour(s) | 2025-11-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
366 | Post-Refresh Validation | Creation of opportunity from the account | 1 hour(s) | 2025-11-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
367 | Post-Refresh Validation | Creation of Sales Quote | 1 hour(s) | 2025-11-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
368 | Post-Refresh Validation | External Pricing from the Sales Quote | 1 hour(s) | 2025-11-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
369 | Post-Refresh Validation | Sales Order Creation | 1 hour(s) | 2025-11-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
370 | Post-Refresh Validation | External Pricing from the Sales Order | 1 hour(s) | 2025-11-03 | 2025-11-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
371 | Post-Refresh Validation | Transfer the Sales Order | 1 hour(s) | 2025-12-03 | 2025-12-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
372 | Post-Refresh Validation | Convey the successful completion of validations. | 10 minute(s) | 2025-12-03 | 2025-12-03 | C4C | Damodara | Nishtha | Verify the business scenarios and take a screenshot of the operational conditions.
373 | Post-Refresh Validation | Create/Change /display Bill of Material | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
374 | Post-Refresh Validation | Display Multilevel BOM | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
375 | Post-Refresh Validation | BOM where-used List | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
376 | Post-Refresh Validation | Creare/change /display WorkCenter | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
377 | Post-Refresh Validation | Create/change/display Routing | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
378 | Post-Refresh Validation | Create/Change/Display Production Version | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
379 | Post-Refresh Validation | Create/change/dispaly Batch | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
380 | Post-Refresh Validation | Create/change/display Production Order (Also Release ,TECO) | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
381 | Post-Refresh Validation | Confirm the Production order - Operation wise | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
382 | Post-Refresh Validation | Confirm the Production order - Order wise | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
383 | Post-Refresh Validation | Goods Issue to production order | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
384 | Post-Refresh Validation | Goods Receipt for Production Order | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
385 | Post-Refresh Validation | Cancel Confirmation of Production Order | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
386 | Post-Refresh Validation | Display Production order confirmation | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
387 | Post-Refresh Validation | Production order information system | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
388 | Post-Refresh Validation | Production Order Predefined Processes execution | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
389 | Post-Refresh Validation | Reprocessing Production Order Confirmations | 30 minute(s) | 2025-10-03 | 2025-10-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
390 | Post-Refresh Validation | Reprocessing Production Order Actual Costs | 30 minute(s) | 2025-11-03 | 2025-11-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
391 | Post-Refresh Validation | Reprocessing Production Order Goods Movements | 30 minute(s) | 2025-11-03 | 2025-11-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
392 | Post-Refresh Validation | Massprocessig of Production Orders | 30 minute(s) | 2025-11-03 | 2025-11-03 | PP | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
393 | Post-Refresh Validation | Production Order Entry Creation for Tiles (Order Creation/Confirm/GR Reversal/Delete) | 30 minute(s) | 2025-11-03 | 2025-11-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
394 | Post-Refresh Validation | Validation,Distribution,Posting of Prodcution Orders for Tiles (Including Reversal of Posting,Distribution and Validation) | 30 minute(s) | 2025-11-03 | 2025-11-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
395 | Post-Refresh Validation | BOM Exception Report | 30 minute(s) | 2025-11-03 | 2025-11-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
396 | Post-Refresh Validation | Report for prod report_tiles_LTP | 30 minute(s) | 2025-11-03 | 2025-11-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
397 | Post-Refresh Validation | Production Statistics | 30 minute(s) | 2025-12-03 | 2025-12-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
398 | Post-Refresh Validation | Production Report Tiles | 30 minute(s) | 2025-12-03 | 2025-12-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
399 | Post-Refresh Validation | Production Order Execution for Sanitaryware Creation (Order Creation/Confirm/GR Reversal/Delete) | 30 minute(s) | 2025-12-03 | 2025-12-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
400 | Post-Refresh Validation | Production Entry details -Validation/Distrubution/Posting - Sanitaryware (Including Reversal of Posting,Distribution and Validation) | 30 minute(s) | 2025-12-03 | 2025-12-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
401 | Post-Refresh Validation | Production Entry report Sanitaryware | 30 minute(s) | 2025-12-03 | 2025-12-03 | pp | Chand basha | Chand basha | Verify the business scenarios and take a screenshot of the operational conditions.
402 | Data Refresh | SAP Copies the C4C production tenant to the C4C Quality tenant | 12 hour(s) | 2025-03-08 | 2025-03-08 | SAP | SAP | SAP
403 | Post-Refresh Validation | Sales order replicated in S/4 | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
404 | Post-Refresh Validation | CHECK FREE STOCK IN ZP_BATCH_STOCK REPORT FOR RELEVANT PACKCODE AND BATCH, IF STOCK IS AVAILABLE THEN DO RESERVATION | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
405 | Post-Refresh Validation | Check and click on posting button, system will generate posting document number | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
406 | Post-Refresh Validation | confirm qty in sales order, | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
407 | Post-Refresh Validation | If there is credit check system will check for credit release | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
408 | Post-Refresh Validation | Credit release sales order | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
409 | Post-Refresh Validation | Create delivery with reference to sales order and do PGI | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
410 | Post-Refresh Validation | Create sales invoice with reference to delivery number | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
411 | Post-Refresh Validation | Accounting document of invoice | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
412 | Post-Refresh Validation | Document flow of sales order -- invoice | 35 minute(s) | 2025-10-03 | 2025-10-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
413 | Post-Refresh Validation | Print invoice | 35 minute(s) | 2025-11-03 | 2025-11-03 | SD | Ramesh | Ramesh/Abhishek | Verify the business scenarios and take a screenshot of the operational conditions.
414 | Post-Refresh Validation | ADD SALES ORDER IN LOADING PLAN | 35 minute(s) | 2025-11-03 | 2025-11-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
415 | Post-Refresh Validation | QTY CONFIRM WITH WAREHOUSE | 35 minute(s) | 2025-11-03 | 2025-11-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
416 | Post-Refresh Validation | VEHICLE PLAN | 35 minute(s) | 2025-11-03 | 2025-11-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
417 | Post-Refresh Validation | Delivery note created | 35 minute(s) | 2025-12-03 | 2025-12-03 | SD | Dinesh | RAKC | Access to confirmed or to reach Dinesh for this
418 | Pre-Refresh Validation | Add/create matrix of document as per the company code | 30 minute(s) | 2025-06-03 | 2025-06-03 | SD | Dinesh | RAKC | Get confirmed from SD team
419 | Post-Refresh Validation | Connectivity Checks | 3 hour(s) | 2025-10-03 | 2025-10-03 | CPI | Sravan | Aparna | Validating the connectivity between S/4HANA and C4C and capture the screenshots. Need to align with Basis team
420 | Post-Refresh Validation | Restore the existing iflows/urls | 2 hour(s) | 2025-10-03 | 2025-10-03 | CPI | Srvana | Aparna | Extract the existing iflows along with urls
421 | Post-Refresh Validation | Validating the IDOC and RFC settings | 2 hour(s) | 2025-11-03 | 2025-11-03 | PI | Sravan | Aparna | Validating the PI interfaces. Need to align with basis team
422 | Post-Refresh Validation | 3rd party systems check(Maxoptra, NeTIX/NETEDI) | 2 hour(s) | 2025-12-03 | 2025-12-03 | PI | Sravan | Aparna
423 | Pre-Refresh validation | RFC connections check | 30 minute(s) | 2025-06-03 | 2025-06-03 | MDG | Mamatha | Mamatha | To align with Aby
424 | Pre-Refresh Validation | Partner Profiles check | 45 minute(s) | 2025-07-03 | 2025-07-03 | MDG | Mamatha | Mamatha | To align with Aby
425 | Post-Refresh Validation | RFC connection check | 30 minute(s) | 2025-10-03 | 2025-10-03 | MDG | Mamatha | Mamatha
426 | Post-Refresh validation | Partner profile check | 45 minute(s) | 2025-11-03 | 2025-11-03 | MDG | Mamatha | Mamatha
427 | Pre-Refresh Validation | Goods Issue to Cost Center | 15 mins | 2025-05-03 | 2025-05-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
428 | Pre-Refresh Validation | Scrapping in Cost Center | 15 mins | 2025-05-03 | 2025-05-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
429 | Pre-Refresh Validation | Goods Receipt against Production Order | 30 mins | 2025-06-03 | 2025-06-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
430 | Pre-Refresh Validation | Goods Receipt for initial entry of stock for warehouse | 45 mins | 2025-05-03 | 2025-05-03 | WM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
431 | Pre-Refresh Validation | Transfer in between Plant to Plant | 30 mins | 2025-06-03 | 2025-06-03 | MM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
432 | Pre-Refresh Validation | Physical Inventory | 45 mins | 06/03.2025 | 06/03.2025 | WM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
433 | Pre-Refresh Validation | LOCAL PO POR-Consumable Purchase | 30 Mins | 2025-06-03 | 2025-06-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
434 | Pre-Refresh Validation | Service Purchase Order | 45 Mins | 2025-07-03 | 2025-07-03 | MM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
435 | Post-Refresh Validation | Goods Issue to Cost Center | 15 mins | 2025-10-03 | 2025-10-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
436 | Post-Refresh Validation | Scrapping in Cost Center | 15 mins | 2025-10-03 | 2025-10-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
437 | Post-Refresh Validation | Goods Receipt against Production Order | 30 mins | 2025-10-03 | 2025-10-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
438 | Post-Refresh Validation | Goods Receipt for initial entry of stock for warehouse | 45 mins | 2025-10-03 | 2025-10-03 | WM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
439 | Post-Refresh Validation | Transfer in between Plant to Plant | 30 mins | 2025-10-03 | 2025-10-03 | MM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
440 | Post-Refresh Validation | Physical Inventory | 45 mins | 2025-11-03 | 2025-11-03 | WM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
441 | Post-Refresh Validation | LOCAL PO POR-Consumable Purchase | 30 Mins | 2025-11-03 | 2025-11-03 | MM | Kirtish | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
442 | Post-Refresh Validation | Service Purchase Order | 45 Mins | 2025-12-03 | 2025-12-03 | MM | Pranita | Kirtish/Pranita | Verify the business scenarios and take a screenshot of the operational conditions.
443 | Pre-Refresh Validation | SOP process for India | 60 minute(s) | 2025-07-03 | 2025-07-03 | PP | Chand basha | Chand basha
444 | Post-Refresh Validation | Mitigation Plan if something doesn't work with SCOS Automation | 1 hour | 2025-05-03 | 15/3/2025 | Basis | Shalaka/Shramik | Shalaka | We already captured all the necessary data, if required configs and settings it will be restored manually
445 | Pre-Refresh Validation | Milestone meetings - Planning, Pre Refresh, Data Refresh, Post Refresh, Closure | 2 Days | 2025-05-03 | 15/3/2025 | PM | Damodara/Shoaib | Santosh/Tamer
446 | Post-Refresh Validation | Add/create matrix of document as per the company code | 35 minute(s) | 2025-12-03 | 2025-12-03 | SD | Dinesh | RAKC | Get confirmed from SD team
447 | Pre-Refresh Validation | All the open transports worked by CG and not moved Production to be tracker as it will be reset during refersh, and to be tested again | 1 Day | 26/02/2025 | 2025-07-03 | Basis | Shalaka | Shalaka | Verify the business scenarios and take a screenshot of the operational conditions.
448 | Pre-Refresh Validation | All the open transports not worked by CG to be taken care by RAKC Change Maanger | 1 Day | 26/02/2025 | 2025-07-03 | RAKC | RAKC | RAKC | Verify the business scenarios and take a screenshot of the operational conditions.
449 | Pre-Refresh Validation | Exceptional Operation changes movement during refresh | 2 Hours | 2025-05-03 | 15/3/2025 | Basis | Shalaka | Shalaka | Verify the business scenarios and take a screenshot of the operational conditions.